**Tasks and Times**

|  |  |  |  |
| --- | --- | --- | --- |
| **Task** | **Responsible** | **Due date** | **Comments** |
| Getting to know database | GJ, Sam | Feb. 15 | If you have any questions, ask! |
| Journal search | GJ, Sam, Szilvi | Feb. 15 | Let’s all compile a list based on relevance and IF, ok? Then Szilvi will make a “best of” list and we will decide from those… |
| Decide on journal | GJ, Sam, Szilvi | Feb. 18 |  |
| Journal requirements, format | Szilvi | Feb. 18 | Gathering info on what requirements, structure, etc. we need to follow |
| Descriptive stats | GJ |  |  |
| Network results | Sam |  |  |
| Introduction: general | Szilvi | Feb.25 |  |
| Introduction: network stuff | GJ |  | Why we are using this analysis, what has been done so far on attitudes, what questions will this address, etc. |
| Methods write-up: survey stuff | Szilvi | Feb.25 | Is it okay if I send GJ the info in note form and he puts it into sentences? |
| Methods write-up: network | Sam |  |  |
| Results write-up: descriptive stats | GJ |  |  |
| Results write-up: network stuff | Sam |  |  |
| Discussion write-up | Szilvi | *pending* | 2 weeks after I see the results |
| Discussion discussion | GJ, Sam, Szilvi |  | 1 week after discussion write-up (appearin conference on what we have so far and conclusions we can draw) |
| Conclusions write-up | Szilvi | *pending* | 1 week after discussion discussion |
| SUM discussion | GJ, Sam, Szilvi |  | Appearin discussion on whole article draft |
| Finalize | Szilvi | *pending* | Revisions based on discussion |
| Submit | Szilvi |  |  |